## PERT Estimation
PERT (Program Evaluation and Review Technique) Estimation
Unit
Functional blocks
# | Name | Optimistic | Most Likely | Pessimistic | Assumptions and comments | Expected | Standard Deviation (sigma) | Variance | One-point Estimate
1 | [5 empty] | 0 | 0 | 0 | #DIV/0!
2 | [5 empty] | 0 | 0 | 0 | #DIV/0!
3 | [5 empty] | 0 | 0 | 0 | #DIV/0!
4 | [5 empty] | 0 | 0 | 0 | #DIV/0!
5 | [5 empty] | 0 | 0 | 0 | #DIV/0!
6 | [5 empty] | 0 | 0 | 0 | #DIV/0!
7 | [5 empty] | 0 | 0 | 0 | #DIV/0!
8 | [5 empty] | 0 | 0 | 0 | #DIV/0!
9 | [5 empty] | 0 | 0 | 0 | #DIV/0!
10 | [5 empty] | 0 | 0 | 0 | #DIV/0!
11 | [5 empty] | 0 | 0 | 0 | #DIV/0!
12 | [5 empty] | 0 | 0 | 0 | #DIV/0!
13 | [5 empty] | 0 | 0 | 0 | #DIV/0!
14 | [5 empty] | 0 | 0 | 0 | #DIV/0!
15 | [5 empty] | 0 | 0 | 0 | #DIV/0!
16 | [5 empty] | 0 | 0 | 0 | #DIV/0!
17 | [5 empty] | 0 | 0 | 0 | #DIV/0!
18 | [5 empty] | 0 | 0 | 0 | #DIV/0!
19 | [5 empty] | 0 | 0 | 0 | #DIV/0!
20 | [5 empty] | 0 | 0 | 0 | #DIV/0!
21 | [5 empty] | 0 | 0 | 0 | #DIV/0!
22 | [5 empty] | 0 | 0 | 0 | #DIV/0!
23 | [5 empty] | 0 | 0 | 0 | #DIV/0!
24 | [5 empty] | 0 | 0 | 0 | #DIV/0!
TOTAL | [5 empty] | 0 |  | 0 | #DIV/0!
Estimation Results
|  | +/-1 sigma (Probability 68,26%) | +/-2 sigma (Probability 95,46%) | +/-3 sigma (Probability 99,73%)
Min |  | 0 | 0 | 0
Expected (Probability 50%) |  | 0
Max |  | 0 | 0 | 0
Note on B2: akoretsky: Unit of Measure (Man-day, Man-hour, Ideal Day, Story point or other)
Note on C4: akoretsky: This estimate is valid if the project situation is ideal, no risks occur
Note on D4: akoretsky: Realistic estimate
Note on E4: akoretsky: This estimate is valid if all possible risks occur
Note on D37: Alexey Koretsky: Recommended value for one-point estimate

## Guidelines
# | Step
1 | Select and enter Unit (Man-day, Man-hour, Ideal Day, Story Point or other).
2 | Decompose the system on several functional blocks. There should be enough functional blocks for effective usage of PERT heuristics. Recommended number of items is more than 15.
3 | For each item enter optimistic, most likely, pessimistic estimate, and assumptions.
4 | "Estimation Results" table contains 3 suggested by PERT ranges. Recommended range is "+/-2 sigma (Probability 95,46%)".